## Folha1
TO DO | IN PROGRESS | REVIEWING | DONE
|  |  | Fork Project (Francisco) |  | Bernardo | Francisco | Inacio | Martin | Carlos
|  |  | Clone project (Martin) | Reviews Done: | 2 | 1 | 0 | 0 | 0
Clone project (Francisco)
Clone project (Bernardo)
Clone project (Carlos)
Clone project (Inácio)
Bernardo's code smells ( Martin, Inacio)
Bernardo's design patterns (Carlos, Inacio)
Carlos' code smells (Martin, Francisco)
Carlos' design patterns
Martin's code smells
Martin's design patterns
Inacio's code smells (Martin, Francisco)
Inacio's design patterns (Carlos)
Francisco's code smells (Carlos)
Francisco's design patterns (Inacio, Martin)
Create final report
Check project specifications and submit