## Folha1
TO DO		IN PROGRESS		REVIEWING		DONE
						Added tab planner (Francisco, Pedro)		Francisco and pedro made pair-programming during this sprint
						Added functions needed for the burndown chart information gathering (Pedro, Pedro)
						Added button for showing the burdown chart (Pedro, Francisco)
						Made necessary changes to the project to start this change (francisco, Pedro)		Note: at this point we made a meeting and decided to change the way we were going to approach the problem, making it into plugins instead of hardcoding the features into the project
						Created class that draws the burndownChart (Carlos)
						Develop PlannerStatistics (Batalaia)
						Further implement burndownChart correctly into program (Carlos)
						continue developing plannerStatistics (Martin)
						Finish graph part (batalaia)